## Tasks
Task_Name | Duration
Create Plan | 2 days
Plan Approval | 5 days
Request Permits | 1 day
Obtain Permits | 6 days
Renovate Board Room | 13 days
Paint Board Room | 3 days
Paint Trim | 1 day
Paint Walls | 1 day
Paint Doors | 1 day
Trim Board Room | 3 days
Install Light Fixtures | 1 day
Install Curtains | 2 days
Lay Carpets in Board Room | 2 days
Install Board Room Furniture | 1 day
Board Room Complete | 0 days
Update Computer Room | 13 days
Electrical Adjust. - Computer Room | 2 days
Install Network Cable | 1 day
Paint Computer Room | 2 days
Lay Carpet in Computer Room | 2 days
Install Computer Room Furniture | 1 day
Install Computers | 4 days